## Sheet1
Task Group	Status	Time Needed	Urgency	Description
Questionnaire	TODO		3	Epoch: How do people currently store time intervals? What is convenient input form
	TODO		3	ParamSizes: How many mice, sessions, trials, color channels, brain layers, ROIs people typically have (simultaneously)
Design	TODO		3	Formalize folder structure. Include raw data, nwb files, results and temporary files
	TODO		3	Formalize storage of global analysis (e.g. statistics over all mice)
	TODO		3	Formalize paths to raw data (e.g. relative to .nwb file)
	TODO		3	Decide on ND traces array storage. Do we store 2D arrays [channel x time], and superimpose other parameters in variable name (pia), or store higher dimensional arrays
	TODO		3	Decide what data types actually necessary. What data types need to be implemented
Interface	Done			Data tab disabled until new/open file
	Done			Save clears QtreeWidgets
	Done			Change design to allow pulling existing subsections from the file
	Done			Investigate if treeview can have combobox as values
	Done			Auto-adjust combo boxes on data load
	TODO	5min	2	Disable save and saveas until new/open file
	TODO	5min	2	Second combo box disabled if first is in mode <Select Stage>
	TODO	15min	2	QTreeWidget values editable, names not editable
	TODO	1h	3	Show parameters in QTreeWidget
	TODO	15min	3	Display pulled features in featureTreeView
	TODO	1h	3	Fill MetaTree existing feature on click
	TODO	4h	3	Implement QComboBox MetaTree items for each @ parameter. Fill values from pull. Complain instead if pull did not succeed
	TODO	4h	3	Decide and implement save procedure for metadata (via apply→save or directly save)
	TODO	4h	2	Design protocol for list-construction (e.g. multiple electrodes at a time)
	TODO	1h	2	Underline (yellow) autofilled places in metadata and data until edited, saved or cleared.
	TODO	15min	2	Underline (red) places that can not be autofilled because they depend on structure (e.g. electrode_group depends on selecting an existing device)
Parameters	Done			Create parameter files
	Done			Load data from parameter file to interface
	Done			Note selection-objects with @ in .json
PYNWB	Done			New creates new file
	Done			Save writes metadata to file.
	Done			Save as creates new file and calls Save
	Done			Open loads basic metadata to containers
	Done			datetime.now() coherence with pynwb
	Done			Ensure the time that is saved is actually time and not string
	TODO	4h	3	Implement "pull" from all existing features with a given name (e.g. @device)
	TODO	???	1	Help->Info presents basic info about the file - type and quantity of data stored
	TODO	4h	3	Learn how to load, save, and rewrite datasets in PYNWB
	TODO	1h	3	Learn how to store links to raw data files.
DataTypes	Done			Add a hierarchy of all useful data types.
	TODO	1h	3	Learn how to do pynwb extensions
	TODO	1h	3	Learn how H5 handles 3D arrays

Import-Raw	TODO	1h	2	Auto-detect image size, channels (gray/rgb)
	TODO	1h	2	Auto-detect video size, channels (gray/rgb), framerate
	TODO		2	Video files in order of importance ::: tiff (stacked), avi, ...
Import-Matlab	Done	15min	3	Converter to import basic 2D matrices from .mat files
	TODO	4h	2	Interface to import several .mat files in a row alphabetically. Specify additional parameters to init names in a loop
	TODO	4h	3	Converter to import 3D .mat files [trace x time x activity]